## CityCare Timeline
CityCare — Full Git Commit Timeline
Public Healthcare & Hospital Management System · Spring Boot 3.3.4 · Java 21 · MySQL · JJWT 0.12.6 · SpringDoc 2.5.0
M1 (Auth / Foundation) · M2 (Citizens / Admin / Facilities) · M3 (Emergency / Dispatch) · M4 (Patients / Treatments / Compliance) · ✓ Done ☐ Pending
WEEK 1 Project Skeleton & Foundation
Days 1–7 · Branch: feature/foundation (M1 leads — all members study the base)
Done | # | Who | Branch | Commit Message | Files Touched
TRUE | C01 | M1 | feature/foundation | chore: initialize Spring Boot project with pom.xml, .gitignore, and README | pom.xml, .gitignore, README.md
TRUE | C02 | M1 | feature/foundation | chore: configure application.properties — DB, JWT secret, port 9090, context-path /api | src/main/resources/application.properties
TRUE | C03 | M1 | feature/foundation | feat: add BaseEntity with @MappedSuperclass, createdAt, updatedAt via Spring Auditing | entity/BaseEntity.java
TRUE | C04 | M1 | feature/foundation | feat: add ApiResponse<T> generic wrapper for all controller responses | dto/response/ApiResponse.java
TRUE | C05 | M1 | feature/foundation | feat: add exception classes — ResourceNotFoundException, BadRequestException, DataNotFoundException, CapacityExceededException, InvalidDataException, UnauthorizedAccessException | exception/*.java
TRUE | C06 | M1 | feature/foundation | feat: add GlobalExceptionHandler with @RestControllerAdvice — handles @Valid, custom exceptions, and 500s | exception/GlobalExceptionHandler.java
TRUE | C07 | M1 | feature/foundation | feat: add User entity with Role enum (ADMIN, STAFF, CITIZEN) and Status enum | entity/User.java
TRUE | C08 | M1 | feature/foundation | feat: add UserRepository with existsByEmail and findByEmail custom queries | repository/UserRepository.java
TRUE | C09 | M1 | feature/foundation | feat: add CityCareApplication entry point with @EnableJpaAuditing | CityCareApplication.java
TRUE | C10 | → main | main | 🔀 Merge feature/foundation → main [M1 shares base — all members fork from here] | —
WEEK 2 All Entities, DTOs & JWT Infrastructure
Days 8–14 · All 4 members on their own branches simultaneously
Done | # | Who | Branch | Commit Message | Files Touched
TRUE | C11 | M1 | feature/auth | feat: add JWTService — generateToken, validateToken, extractUserName using JJWT 0.12.6 | service/JWTService.java
TRUE | C12 | M1 | feature/auth | feat: add UserDetailsServiceImpl — load user by email for Spring Security | security/UserDetailsServiceImpl.java
TRUE | C13 | M1 | feature/auth | feat: add JwtFilter extending OncePerRequestFilter — parse Bearer token, set SecurityContext | JwtFilter/JwtFilter.java
TRUE | C14 | M1 | feature/auth | feat: add SecurityConfig — stateless JWT filter chain, BCrypt(12), CORS, role-based route guards | config/SecurityConfig.java
TRUE | C15 | M1 | feature/auth | feat: add LoginRequest, RegisterRequest DTOs and AuthResponse with userId, name, email, role | dto/request/LoginRequest.java, dto/request/RegisterRequest.java, dto/response/AuthResponse.java
TRUE | C16 | M2 | feature/citizens-admin | feat: add Citizen entity linked to User @ManyToOne LAZY — name, contactInfo, status | entity/Citizen.java
TRUE | C17 | M2 | feature/citizens-admin | feat: add CitizenDocument entity for citizen file uploads with filePath and fileType | entity/CitizenDocument.java
TRUE | C18 | M2 | feature/citizens-admin | feat: add Staff entity with role, facilityId reference, and User FK | entity/Staff.java
TRUE | C19 | M2 | feature/citizens-admin | feat: add Facility entity with type, capacity, currentOccupancy, and status | entity/Facility.java
TRUE | C20 | M2 | feature/citizens-admin | feat: add request DTOs — CitizenProfileRequest, FacilityRequest, CreateStaffRequest, UpdateStaffFacilityRequest | dto/request/*.java
TRUE | C21 | M3 | feature/emergency | feat: add Emergency entity with type, location, status (PENDING/DISPATCHED/RESOLVED), reportedBy | entity/Emergency.java
TRUE | C22 | M3 | feature/emergency | feat: add Ambulance entity with vehicleNumber and AmbulanceStatus (AVAILABLE/BUSY) | entity/Ambulance.java
TRUE | C23 | M3 | feature/emergency | feat: add AmbulanceDispatch entity linking Emergency to Ambulance with dispatchedAt timestamp | entity/AmbulanceDispatch.java
TRUE | C24 | M3 | feature/emergency | feat: add EmergencyRequest, AmbulanceRequest, DispatchRequest DTOs | dto/request/EmergencyRequest.java, dto/request/AmbulanceRequest.java, dto/request/DispatchRequest.java
TRUE | C25 | M4 | feature/patients-compliance | feat: add Patient entity with admissionDate, status (ADMITTED/DISCHARGED), and citizenId FK | entity/Patient.java
TRUE | C26 | M4 | feature/patients-compliance | feat: add Treatment entity with diagnosis, prescription, treatedBy, and Patient FK | entity/Treatment.java
TRUE | C27 | M4 | feature/patients-compliance | feat: add ComplianceRecord entity for entity-level compliance tracking | entity/ComplianceRecord.java
TRUE | C28 | M4 | feature/patients-compliance | feat: add Audit and AuditLog entities for action history tracking | entity/Audit.java, entity/AuditLog.java
TRUE | C29 | M4 | feature/patients-compliance | feat: add AdmitPatientRequest, TreatmentRequest, TreatmentSummaryResponse, ComplianceRecordRequest, AuditRequest DTOs | dto/request/*.java, dto/request/TreatmentSummaryResponse.java
TRUE | C30 | → main | main | 🔀 Merge all feature branches → main [Verify all Hibernate tables created in MySQL before continuing] | —
WEEK 3 Repositories & Service Layer
Days 15–21 · Business logic — the core of the application
Done | # | Who | Branch | Commit Message | Files Touched
TRUE | C31 | M1 | feature/auth | feat: implement AuthService — register with BCrypt, auto-create Citizen on register, login with JWT via JWTService | service/AuthService.java
TRUE | C32 | M1 | feature/auth | test: verify register auto-creates citizen row — login and hit /citizens/profile via Swagger | — (manual test checkpoint)
TRUE | C33 | → main | main | 🔀 Merge feature/auth → main [JWT security live — all members can now protect their routes] | —
TRUE | C34 | M2 | feature/citizens-admin | feat: add CitizenRepository (findByUser) and CitizenDocumentRepository (findByCitizen) | repository/CitizenRepository.java, repository/CitizenDocumentRepository.java
TRUE | C35 | M2 | feature/citizens-admin | feat: add StaffRepository (findByFacilityId) and FacilityRepository (findByType, findByStatus) | repository/StaffRepository.java, repository/FacilityRepository.java
TRUE | C36 | M2 | feature/citizens-admin | feat: implement CitizenService — getProfile, updateProfile, upload and list documents | service/CitizenService.java
TRUE | C37 | M2 | feature/citizens-admin | feat: implement FacilityService — create, getAll, getById, update, filterByTypeAndStatus | service/FacilityService.java
FALSE | C38 | M2 | feature/citizens-admin | feat: implement AdminService — createStaff, assignFacility, registerAmbulance, listUsers | service/AdminService.java
TRUE | C39 | M3 | feature/emergency | feat: add EmergencyRepository (findByStatus, findByReportedBy) and AmbulanceRepository (findByStatus) | repository/EmergencyRepository.java, repository/AmbulanceRepository.java
TRUE | C40 | M3 | feature/emergency | feat: add AmbulanceDispatchRepository with findByEmergencyId lookup | repository/AmbulanceDispatchRepository.java
TRUE | C41 | M3 | feature/emergency | feat: implement EmergencyService — reportEmergency, listPending, dispatchAmbulance, resolveEmergency | service/EmergencyService.java
FALSE | C42 | M3 | feature/emergency | fix: set ambulance to BUSY on dispatch, AVAILABLE on resolution — add availability guard | service/EmergencyService.java
FALSE | C43 | M4 | feature/patients-compliance | feat: add PatientRepository (findByStatus) and TreatmentRepository (findByPatientId, findByTreatedBy) | repository/PatientRepository.java, repository/TreatmentRepository.java
FALSE | C44 | M4 | feature/patients-compliance | feat: add ComplianceRecordRepository and AuditRepository with entity-based lookups | repository/ComplianceRecordRepository.java, repository/AuditRepository.java, repository/AuditLogRepository.java
FALSE | C45 | M4 | feature/patients-compliance | feat: implement PatientService — admitPatient, getAllPatients, filterByStatus, getById | service/PatientService.java
FALSE | C46 | M4 | feature/patients-compliance | feat: implement TreatmentService — addTreatment, listByPatient, listOwnTreatments, getTreatmentSummary | service/TreatmentService.java
FALSE | C47 | M4 | feature/patients-compliance | feat: implement ComplianceService — createRecord, createAudit, getAuditLogs, getRecordsByEntity | service/ComplianceService.java
FALSE | C48 | → main | main | 🔀 Merge all feature branches → main [Full service layer complete — business logic done] | —
WEEK 4 Controllers, Integration & Final Polish
Days 22–30 · Wire everything up, test end-to-end, and ship
Done | # | Who | Branch | Commit Message | Files Touched
FALSE | C49 | M1 | feature/auth | feat: add AuthController — POST /auth/register and POST /auth/login, returns JWT token | controller/AuthController.java
FALSE | C50 | M1 | feature/auth | test: end-to-end auth flow — register, login, use JWT Bearer on protected /citizens/profile | — (manual test checkpoint)
FALSE | C51 | → main | main | 🔀 Merge feature/auth → main [AuthController live — all endpoints now require valid JWT] | —
FALSE | C52 | M2 | feature/citizens-admin | feat: add CitizenController — GET /citizens/profile, PUT /citizens/profile, GET /citizens/{id}, document upload/list | controller/CitizenController.java
FALSE | C53 | M2 | feature/citizens-admin | feat: add FacilityController — full CRUD on /facilities, filter by type and status | controller/FacilityController.java
FALSE | C54 | M2 | feature/citizens-admin | feat: add AdminController — POST /admin/staff, POST /admin/ambulances, GET /admin/users | controller/AdminController.java
FALSE | C55 | M2 | feature/citizens-admin | test: role-based access check — ADMIN-only routes reject CITIZEN JWT with 403 | — (manual test checkpoint)
FALSE | C56 | M3 | feature/emergency | feat: add EmergencyController — POST /emergencies/report, GET /emergencies/pending, POST /emergencies/{id}/dispatch, GET /emergencies/mine | controller/EmergencyController.java
FALSE | C57 | M3 | feature/emergency | test: full dispatch flow — report → list pending → dispatch → verify ambulance is BUSY | — (manual test checkpoint)
FALSE | C58 | M3 | feature/emergency | fix: throw ResourceNotFoundException (404) when emergencyId not found in dispatch endpoint | controller/EmergencyController.java, service/EmergencyService.java
FALSE | C59 | M4 | feature/patients-compliance | feat: add PatientController — POST /patients/admit, GET /patients, GET /patients/{id}, filter by status | controller/PatientController.java
FALSE | C60 | M4 | feature/patients-compliance | feat: add TreatmentController — POST /treatments, GET /treatments/patient/{id}, GET /treatments/mine, GET /treatments/summary/{id} | controller/TreatmentController.java
FALSE | C61 | M4 | feature/patients-compliance | feat: add ComplianceController — CRUD on /compliance/records and /audits, GET /compliance/logs | controller/ComplianceController.java
FALSE | C62 | M4 | feature/patients-compliance | test: admit-to-treat flow — admit citizen as patient, add treatment, verify compliance record created | — (manual test checkpoint)
FALSE | C63 | → main | main | 🔀 Merge all feature branches → main [All controllers live — full REST API functional] | —
FALSE | C64 | M1 | feature/final-polish | fix: add data.sql — seed ADMIN/STAFF/CITIZEN users, sample facility, ambulance records | src/main/resources/data.sql
FALSE | C65 | M2 | feature/final-polish | fix: throw BadRequestException on duplicate citizen profile creation in CitizenService | service/CitizenService.java
FALSE | C66 | M3 | feature/final-polish | fix: throw CapacityExceededException in FacilityService when currentOccupancy exceeds capacity | service/FacilityService.java
FALSE | C67 | M4 | feature/final-polish | fix: throw DataNotFoundException (404) when patient not found in TreatmentService | service/TreatmentService.java
FALSE | C68 | M1 | feature/final-polish | docs: update README with setup steps, JWT usage, Swagger URL (/api/swagger-ui.html), and sample curls | README.md
FALSE | C69 | M1 | feature/final-polish | chore: add CityCareApplicationTests — context loads, H2 in-memory for test profile | src/test/resources/application.properties, CityCareApplicationTests.java
FALSE | C70 | → main | main | 🔀 Merge feature/final-polish → main [🚀 CityCare v1.0 — fully developed REST API] | —
Commit Summary
M1 — 18 commits | M2 — 14 commits | M3 — 12 commits | M4 — 15 commits | → main — 5 merges
Total: 70 commits · 5 merge-to-main milestones · 1 fully working Spring Boot REST API · CityCare v1.0