## CityCare Timeline
CityCare — Full Git Commit Timeline
Every commit, every member, branch-by-branch — from skeleton to fully working REST API
M1 (Auth/Foundation) M2 (Citizens/Admin/Facilities) M3 (Emergency/Dispatch) M4 (Patients/Treatments/Compliance) ✓ Already Done
WEEK 1 Project Skeleton & Foundation
Days 1–7 · Branch: feature/foundation (Member 1 leads, everyone studies)
| # | Who | Branch | Commit Message | Files Touched
TRUE | C01 | M1 | feature/foundation | chore: initialize Spring Boot project with README and .gitignore | README.md, .gitignore
TRUE | C02 | M1 | feature/foundation | chore: initial Spring Boot setup with Maven dependencies | pom.xml
TRUE | C03 | M1 | feature/foundation | feat: added BaseEntity, ApiResponse wrapper, and GlobalExceptionHandler | entity/BaseEntity.java, dto/response/ApiResponse.java, exception/GlobalExceptionHandler.java, exception/ResourceNotFoundException.java, exception/BadRequestException.java
TRUE | C04 | M1 | feature/foundation | feat: add User entity with Role enum and UserRepository | entity/User.java, repository/UserRepository.java
TRUE | C05 | M1 | feature/foundation | feat: add CityCareApplication entry point with JPA auditing enabled | CityCareApplication.java
TRUE | C06 | M1 | feature/foundation | chore: configure application.properties (DB, JWT, Swagger, port 9090) | src/main/resources/application.properties
TRUE | C07 | → main | main | 🔀 Merge feature/foundation → main [M1 shares base — all members now fork from here] | —
WEEK 2 All Entities & DTOs
Days 8–14 · All 4 members on their own branches simultaneously
| # | Who | Branch | Commit Message | Files Touched
TRUE | C08 | M1 | feature/auth | feat: add JWT utility class — generate, validate, extract claims | security/JwtUtils.java
TRUE | C09 | M1 | feature/auth | feat: add JwtAuthFilter — intercept requests and set SecurityContext | security/JwtAuthFilter.java
TRUE | C10 | M1 | feature/auth | feat: add UserDetailsServiceImpl — load user by email for Spring Security | security/UserDetailsServiceImpl.java
TRUE | C11 | M1 | feature/auth | feat: add SecurityConfig with JWT filter chain and role-based route rules | config/SecurityConfig.java
TRUE | C12 | M1 | feature/auth | feat: add SwaggerConfig with JWT Bearer auth support | config/SwaggerConfig.java
TRUE | C13 | M1 | feature/auth | feat: add Login and Register request DTOs and AuthResponse | dto/request/LoginRequest.java, dto/request/RegisterRequest.java, dto/response/AuthResponse.java
TRUE | C14 | M2 | feature/citizens-admin | feat: add Citizen entity linked to User with profile fields | entity/Citizen.java
TRUE | C15 | M2 | feature/citizens-admin | feat: add CitizenDocument entity for file uploads per citizen | entity/CitizenDocument.java
TRUE | C16 | M2 | feature/citizens-admin | feat: add Staff entity with role and facility reference | entity/Staff.java
TRUE | C17 | M2 | feature/citizens-admin | feat: add Facility entity with type, capacity, and status fields | entity/Facility.java
TRUE | C18 | M2 | feature/citizens-admin | feat: add request DTOs for citizen, staff, and facility creation | dto/request/CitizenProfileRequest.java, dto/request/FacilityRequest.java, dto/request/CreateStaffRequest.java, dto/request/UpdateStaffFacilityRequest.java
TRUE | C19 | M3 | feature/emergency | feat: add Emergency entity with type, location, and status tracking | entity/Emergency.java
TRUE | C20 | M3 | feature/emergency | feat: add Ambulance entity with vehicleNumber and availability status | entity/Ambulance.java
TRUE | C21 | M3 | feature/emergency | feat: add AmbulanceDispatch entity linking emergency to ambulance | entity/AmbulanceDispatch.java
TRUE | C22 | M3 | feature/emergency | feat: add request DTOs for emergency reporting, ambulance, and dispatch | dto/request/EmergencyRequest.java, dto/request/AmbulanceRequest.java, dto/request/DispatchRequest.java
TRUE | C23 | M4 | feature/patients-compliance | feat: add Patient entity with admission fields and status enum | entity/Patient.java
TRUE | C24 | M4 | feature/patients-compliance | feat: add Treatment entity with diagnosis, doctor, and date | entity/Treatment.java
TRUE | C25 | M4 | feature/patients-compliance | feat: add ComplianceRecord entity for entity-level compliance tracking | entity/ComplianceRecord.java
TRUE | C26 | M4 | feature/patients-compliance | feat: add Audit and AuditLog entities for action history | entity/Audit.java, entity/AuditLog.java
TRUE | C27 | M4 | feature/patients-compliance | feat: add request DTOs for patient admission, treatment, compliance and audit | dto/request/AdmitPatientRequest.java, dto/request/TreatmentRequest.java, dto/request/ComplianceRecordRequest.java, dto/request/AuditRequest.java
TRUE | C28 | → main | main | 🔀 Merge all feature branches → main [Verify all Hibernate tables created in MySQL before continuing] | —
WEEK 3 Repositories & Service Layer
Days 15–21 · Business logic — the core of the application
| # | Who | Branch | Commit Message | Files Touched
TRUE | C29 | M1 | feature/auth | feat: add AuthService — register with BCrypt, login with JWT generation | service/impl/AuthService.java
TRUE | C30 | M1 | feature/auth | test: verify register and login endpoints return correct JWT via Swagger | — (manual test checkpoint)
FALSE | C31 | → main | main | 🔀 Merge feature/auth → main [JWT security now live — all other members can protect their routes] | —
FALSE | C32 | M2 | feature/citizens-admin | feat: add CitizenRepository and CitizenDocumentRepository with custom queries | repository/CitizenRepository.java, repository/CitizenDocumentRepository.java
FALSE | C33 | M2 | feature/citizens-admin | feat: add StaffRepository and FacilityRepository with filter queries | repository/StaffRepository.java, repository/FacilityRepository.java
FALSE | C34 | M2 | feature/citizens-admin | feat: implement CitizenService — create profile, get profile, upload and list documents | service/impl/CitizenService.java
FALSE | C35 | M2 | feature/citizens-admin | feat: implement FacilityService — create, read, update, filter by type and status | service/impl/FacilityService.java
FALSE | C36 | M2 | feature/citizens-admin | feat: implement AdminService — create staff, assign facilities, register ambulances, list users | service/impl/AdminService.java
TRUE | C37 | M3 | feature/emergency | feat: add EmergencyRepository with findByStatus and findByReportedBy queries | repository/EmergencyRepository.java
FALSE | C38 | M3 | feature/emergency | feat: add AmbulanceRepository with findByStatus(AVAILABLE) query | repository/AmbulanceRepository.java
FALSE | C39 | M3 | feature/emergency | feat: add AmbulanceDispatchRepository with dispatch lookup queries | repository/AmbulanceDispatchRepository.java
FALSE | C40 | M3 | feature/emergency | feat: implement EmergencyService — report, list pending, dispatch ambulance, update status | service/impl/EmergencyService.java
FALSE | C41 | M3 | feature/emergency | fix: set ambulance status to BUSY on dispatch and AVAILABLE on resolution | service/impl/EmergencyService.java
TRUE | C42 | M4 | feature/patients-compliance | feat: add PatientRepository, TreatmentRepository with patient and doctor lookup queries | repository/PatientRepository.java, repository/TreatmentRepository.java
TRUE | C43 | M4 | feature/patients-compliance | feat: add ComplianceRecordRepository and AuditRepository with entity-based lookups | repository/ComplianceRecordRepository.java, repository/AuditRepository.java, repository/AuditLogRepository.java
FALSE | C44 | M4 | feature/patients-compliance | feat: implement PatientService — admit patient, list all, filter by status, get by ID | service/impl/PatientService.java
FALSE | C45 | M4 | feature/patients-compliance | feat: implement TreatmentService — add treatment, list by patient, list own treatments | service/impl/TreatmentService.java
FALSE | C46 | M4 | feature/patients-compliance | feat: implement ComplianceService — create records, audits, retrieve logs | service/impl/ComplianceService.java
FALSE | C47 | → main | main | 🔀 Merge all feature branches → main [All services done — full business logic layer complete] | —
WEEK 4 Controllers, Integration & Final Polish
Days 22–30 · Wire everything up, test end-to-end, review and ship
| # | Who | Branch | Commit Message | Files Touched
FALSE | C48 | M1 | feature/auth | feat: add AuthController — POST /auth/register and POST /auth/login | controller/AuthController.java
FALSE | C49 | M1 | feature/auth | test: end-to-end test of full auth flow — register, login, access protected route with JWT | — (manual test checkpoint)
FALSE | C50 | → main | main | 🔀 Merge feature/auth → main [AuthController live — all endpoints now require valid JWT] | —
FALSE | C51 | M2 | feature/citizens-admin | feat: add CitizenController — POST/GET /citizens/profile, GET /{id}, document upload and list | controller/CitizenController.java
FALSE | C52 | M2 | feature/citizens-admin | feat: add FacilityController — full CRUD on /facilities, filter by type and status | controller/FacilityController.java
FALSE | C53 | M2 | feature/citizens-admin | feat: add AdminController — create staff, manage ambulances, list dispatchers and users | controller/AdminController.java
FALSE | C54 | M2 | feature/citizens-admin | test: verify role-based access — ADMIN-only routes reject CITIZEN tokens | — (manual test checkpoint)
FALSE | C55 | M3 | feature/emergency | feat: add EmergencyController — report, list pending, dispatch, get my emergencies | controller/EmergencyController.java
FALSE | C56 | M3 | feature/emergency | test: full dispatch flow — report emergency → list pending → dispatch → verify ambulance status | — (manual test checkpoint)
FALSE | C57 | M3 | feature/emergency | fix: return 404 when emergency ID not found in dispatch endpoint | controller/EmergencyController.java, service/impl/EmergencyService.java
FALSE | C58 | M4 | feature/patients-compliance | feat: add PatientController — POST /admit, GET /patients, filter by status | controller/PatientController.java
FALSE | C59 | M4 | feature/patients-compliance | feat: add TreatmentController — add treatment, list by patient, list own | controller/TreatmentController.java
FALSE | C60 | M4 | feature/patients-compliance | feat: add ComplianceController — full CRUD on /compliance/records and /audits, GET /logs | controller/ComplianceController.java
FALSE | C61 | M4 | feature/patients-compliance | test: admit-to-treat flow — admit citizen as patient, add treatment, verify compliance record | — (manual test checkpoint)
FALSE | C62 | → main | main | 🔀 Merge all feature branches → main [All controllers live — full API functional] | —
FALSE | C63 | M1 | feature/final-polish | fix: add seed data.sql for roles, test users, and sample facilities | src/main/resources/data.sql
FALSE | C64 | M2 | feature/final-polish | fix: handle duplicate citizen profile creation with 400 BadRequestException | service/impl/CitizenService.java
FALSE | C65 | M3 | feature/final-polish | fix: prevent dispatch to already-busy ambulance — add availability check | service/impl/EmergencyService.java
FALSE | C66 | M4 | feature/final-polish | fix: return 404 when patient not found in treatment creation | service/impl/TreatmentService.java
FALSE | C67 | M1 | feature/final-polish | docs: update README with setup steps, Swagger URL, and sample API calls | README.md
FALSE | C68 | M1 | feature/final-polish | chore: update test application.properties and add CityCareApplicationTests | src/test/resources/application.properties, CityCareApplicationTests.java
FALSE | C69 | → main | main | 🔀 Merge feature/final-polish → main [🚀 CityCare v1.0 — fully developed REST API] | —
Commit Summary
M1 — 17 commits | M2 — 14 commits | M3 — 12 commits | M4 — 15 commits
Total: 69 commits across 4 members · 5 merge-to-main milestones · 1 fully working Spring Boot REST API